## Features - Features per state (
Features per state (individual initiative) within Portfolio database
Relevant module |  | clarify and control |  |  |  | Pipeline
Relevant module | receive req | [5 empty] | Start
Feature list (against latest state for when feature arrives) | R | R’ | C | C’ | C’’ | P | P’ | Family | Note | Example
Previous identifier | 1 | [6 empty] | Identification
UUID | 1 | [7 empty] | numeric
STATE IDENTIFIER | 1 | [7 empty] | alpha
Name |  | 1
Business function |  |  |  |  | 1 |  |  | Alignment
Business benefit /justification / 2 line |  |  | 1
Department lead | [5 empty] | 1
Project manager | [6 empty] | 1
Sponsor
Scope (output) ( 2 line) |  | 1 | [5 empty] | Scope
Scope (approach) / 2 line |  |  |  | 1
WBS | [5 empty] | 1
Plan by phase | [7 empty] | Schedule
Estimate | [5 empty] | 1 |  | Cost
Budget | [6 empty] | 1

## Feature ownership - Feature own
Feature ownership (individal initiative)
Feature list (against latest state for when feature arrives) | Rights | Primary Document
Previous identifier | Client or Op Demand | Client sheet
UUID | PMO | PMO request and project database
STATE IDENTIFIER | PMO | PMO request and project database
Name | Originator | Project framework
Business function | Sub-portfolio lead | Project framework
Business benefit /justification / 2 line | Sub-portfolio lead | Project framework
Sub-portfolio | Sub-portfolio lead | Project framework
Project manager | Sub-portfolio lead | Project framework
Sponsor | Sub-portfolio lead | Project framework
Scope (output) ( 2 line) | Originator | Project framework
Scope (approach) / 2 line | Originator | Project framework
WBS
Plan by phase
Estimate
Budget
R->R’

## Transition table - Transition t
Transition table (individual initiative)
| Old State | Condition | New state | Any modified terms | Any new terms | Any features subsequently added or modified by others
| R |  | R’
| R |  | Rejected
| R’ |  | C
| R’ |  | Rejected
| R’ |  | Clarification

## Lists per module - Lists and su
Lists and summaries of relevant memberships
List of all unprocessed requests | Previous identifier | UUID | State
R1 | inherited from Originator | created by PMO
R2
R3
example
List of all R’ requests | Previous identifier | UUID | State | Name | Scope (output) ( 2 line)
R’1 | inherited from PMO database | inherited from PMO database
R’2
R’3
example
Portfolio summary of requests | Number of R | Number of R’ | Number transitioned from R to R’’ this month | Number transitioned from R to R’’ this year | etc
| 3 | 3

## Synch matrix
Table 1
State | Gate
Transition table | Action table
Features | Time states, including the relation between forecast and actual
dates | need dates per each addition and edit etc
convolution | any features added as a result of affect of aggregated features for all initiatives in a given state

## State transitions - Features pe
Features per state (individual initiative)
Feature list (against latest state for when feature arrives) | R | R’ | C | C’ | C’’ | P | P’
R | 1 | 1
R’ |  | 1 | 1
C |  |  | 1 | 1
C’ |  |  |  | 1 | 1
C’’ |  |  |  |  | 1 | 1
P | [5 empty] | 1 | 1
P’ | [6 empty] | 1